## Sheet1
Risk Sections | Risk | Description | Impact | Likelihood | Severity | Mitigation Strategy
Hardware | Power Overload | High current draw from the motors, especially during peak loads, could lead to an overload on the ESC or PCB. | Damage to the PCB, ESC, or motors. Potential fire hazard. | Medium | High | Use ESCs with current, temperature, and voltage monitoring systems to detect and mitigate overloads. Ensure sufficient tolerance by selecting ESCs with higher current ratings than the motors' peak draw.
| PCB Overheating | The integration of multiple components on a single compact PCB could lead to excessive heat generation. | Reduced performance, component damage, and potential system failure. | Medium | High | Ensure the PCB traces are wide enough, Ensure there is proper heat dissipition if necessary use heat sinks
| Motor Failure | Motors could fail due to overuse, wear, or manufacturing defects, especially in extreme conditions. | Reduced flight performance or complete loss of control. | Low | High | Select high-quality motors with proper KV ratings for the flight and cleaning functions. Perform regular maintenance and testing.
| Unbalanced Weight Distribution | Improper balancing of the weight distribution (especially with different motors) could cause unstable flight. | Poor flight performance, overloading certain motors. | Medium | Medium | Carefully plan the layout of the components and ensure the center of gravity is aligned with the drone's center.
| Battery Overload | Excessive current draw from the 6S battery, particularly from motors and other high-power components. | Shortened battery life, overheating, or battery failure. | Medium | High | Use a proper LiPo chargers and ensure proper power distribution via voltage regulators.
| Weight and Payload Management | Adding too many components or excessive weight could reduce flight time or cause the drone to struggle during flight. | Shortened flight time, instability, or failure to lift off. | Medium | High | Carefully optimize the weight of each component and aim to reduce the overall drone weight during design.
| Component Availability | Shortages of components from JLCPCB or other suppliers may cause delays in production. | Project delays and cost overruns. | Medium | Low | Identify backup suppliers and components early in the project. Use components with high availability.
| Component Incompatibility | Some selected components (motors, sensors, controllers) may not be fully compatible with each other in terms of electrical or communication interfaces. | Malfunctions or inability to control the drone effectively. | Low | High | Verify all components' electrical characteristics and protocols during the design phase.
| Soldering and Assembly Errors | Incorrect soldering or poor assembly can cause short circuits, open circuits, or incorrect component connections. | Malfunction of the PCB, failure of the drone system. | Low | Medium | Use professional PCBA services (JLCPCB), ensure detailed documentation for assembly, and verify the design for manufacturing compatibility.
Software | Firmware Bugs (Flight Controller) | Bugs in the flight controller firmware may cause instability in flight or failure to execute commands properly. | Loss of control over the drone, crashes, or instability during operation. | High | High | Conduct thorough testing of the firmware on a physical prototype before full-scale deployment.
| App Communication Failure | Loss of communication between the app and drone (WiFi/BLE) could lead to loss of control or incorrect telemetry data. | Loss of control, delayed or incorrect responses from the drone. | Medium | High | Implement a failsafe mechanism where the drone defaults to safe hover mode if communication is lost.
| Telemetry Data Corruption | Corrupted or delayed telemetry data could cause the app to misinterpret the drone’s status, leading to incorrect commands. | Poor drone control or instability in flight. | Low | Medium | Use reliable data transmission protocols
| AI Integration Issues (Future Development) | Future AI capabilities (e.g., auto window cleaning) may encounter issues in video feed analysis or flight data synchronization. | Poor automation, misinterpretation of sensor data, or incorrect execution of AI-driven tasks. | Low | Medium | Keep the future scope in mind while developing the Drone
| Latency in App Communication | High latency in the communication between the drone and the app could lead to delayed responses or commands being executed too late. | Drone instability, delayed or missed commands. | Medium | High | Use low-latency communication protocols (MSP)
Operational | Environmental Conditions | Wind, rain, or extreme temperatures may affect the drone's performance. | Flight instability, loss of control, or reduced sensor effectiveness. | High | Medium | Design the drone for environmental resilience
| Regulatory Compliance | The drone may face restrictions in certain areas due to airspace regulations. | Limited areas for testing or deployment, potential legal issues. | Low | Medium | Research local regulations and ensure compliance before operation. Obtain necessary licenses or permits for testing and operation.
Window Cleaning Drone Risk Assessment list